## Story Summary
Foundations Trail — Story Summary (regenerated) | One row per story. Regenerated from the Traceability Matrix detail sheet — splits included.
Sprint | Week | Story ID | Story Title | Persona | User Story (summary) | Exam Domain | Exam Wt. | Scenarios | Notes
Sprint 1 | Week 1 | S1-01 | Enhanced Contact Data Capture | Support Staff | Store Utility Account Numbers and Lease Expiration dates on Contact to identify eligibility without external spreadsheets. | Object Manager & Lightning App Builder | ~20% | 3
Sprint 1 | Week 2 | S1-02 | Household Account Mapping | Program Manager | Group individual Contacts under one Household Account to track total impact and service history for a family unit. | Configuration & Setup / NPSP | ~20% | 2
Sprint 1 | Week 3 | S1-03 | Case Privacy & Security Architecture | System Administrator | Set Case OWD to Private and build a role hierarchy so sensitive records are visible only to the assigned caseworker and management. | Security & Access | ~13% | 4
Sprint 1 | Week 4 | S1-04 | Federal Funding Eligibility Tracking | Executive Director | Track Veteran Status and Income Bracket on Contact for federal Community First grant demographic reporting. | Object Manager & Analytics | ~20% / ~9% | 3
Sprint 2 | Week 5 | S2-01 | Multi-Channel Email-to-Case | Support Representative | Emails to three routing addresses automatically become Cases so triage starts without manual transcription. | Service & Support Applications | ~11% | 3 | REVISED — routing addresses now learner plus-addresses; AC-3 retargeted.
Sprint 2 | Week 7 | S2-02 | Automated Queue Routing | Support Representative | Incoming Cases routed automatically to the correct specialist queue by service type so no case sits in the wrong queue. | Sales & Marketing Applications | ~12% | 3 | MOVED from Week 5 to Week 7 — see load note on Week Map.
Sprint 2 | Week 6 | S2-03.a | Public Web-to-Case Intake Form | Community Member in crisis | Submit a help request via a web form so assistance can be requested when the office is closed. | Service & Support Applications | ~11% | 3 | SPLIT parent story. Ships the form and its hidden record type.
Sprint 2 | Weeks 6–7 | S2-03.b | Create Public Case Intake Platform | Community Member in crisis | A public platform that accepts a case submission at the moment of need. | Service & Support Applications | ~11% | 2 | SPLIT child — spans two weeks. Emerged in Cohort 0 testing when the story outgrew its week.
Sprint 2 | Week 7 | S2-04 | Auto-Response & Routing Notifications | Support Representative | Clients automatically receive confirmation when their case is created so they know the request was received. | Service & Support Applications | ~11% | 3 | ANNOTATED — Developer Edition daily email cap documented.
Sprint 2 | Week 8 | S2-05 | Loop Protection Flow (Spam & OOO Filter) | System Administrator | Prevent Out of Office and Undeliverable emails from creating Cases so queues are not flooded with ghost records. | Process Automation & Flow Builder | ~16% | 3 | REVISED — AC-1 conflict resolved to Status = Closed; Constraint Encounter deliverable added.
Sprint 3 | Week 9 | S3-01 | Visual SLA Milestone Tracking | Support Representative | A live countdown on Urgent cases to ensure first response inside the 4-hour target. | Service & Support / Entitlements | ~11% | 4
Sprint 3 | Week 10 | S3-02 | Red Alert Escalation Engine | System Administrator | A scheduled Flow detects Urgent cases unassigned over 2 hours and alerts Elena privately before SLA breach. | Process Automation & Flow Builder | ~16% | 3
Sprint 3 | Week 11 | S3-03 | Donor Impact & Performance Dashboard | Program Director (Elena) | Real-time SLA achievement, case volume and veteran metrics for data-backed donor and board reporting. | Analytics, Reports & Dashboards | ~9% | 4
Sprint 3 | Weeks 10 & 12 | S3-04 | Private Escalation Alerts & Org Handover | Program Manager (Elena) | Escalations as private alerts rather than public Chatter, plus a complete org handover package. | Change Management & Service Cloud | ~7% / ~11% | 4 | Appears in both Week 10 and Week 12 in the Week Map — intentional: alerts in W10, handover in W12.

## Week Map
Foundations Trail — Week x Story Map (regenerated) | Supersedes the Week Map in Traceability Matrix v1.0 and the week tables in Program Blueprint v1.0.
Sprint | Week | Week Title | Stories Active | Primary Exam Domain | Exam Wt. | Definition of Done (summary)
Sprint 1 | Week 1 | Org Setup & Data Discovery | S1-01, S1-02 | Configuration & Setup | ~20% | Org live, NPSP Household Model active, portfolio URL shareable
Sprint 1 | Week 2 | Custom Objects, Fields & Relationships | S1-01, S1-04 | Object Manager & Lightning App Builder | ~20% | Past date rejected; blank date accepted; all fields Required = FALSE
Sprint 1 | Week 3 | Security Architecture | S1-03, S1-04 | Security & Access | ~13% | All 5 security tests pass as expected
Sprint 1 | Week 4 | Data Management & Sprint 1 Demo | S1-01, S1-02, S1-03, S1-04 | Data Management | ~10% | Grant Eligibility Report returns 9 Veterans; import failures documented
Sprint 2 | Week 5 | Case Management & Multi-Channel Intake | S2-01 | Service & Support Applications | ~11% | Test email to each plus-address creates correct Record Type and Queue
Sprint 2 | Week 6 | Web-to-Case & Validation Logic | S2-03.a, S2-03.b (starts) | Service & Support Applications | ~11% | Form submission creates Case in Utility Queue; Contact matched by email
Sprint 2 | Week 7 | Intelligent Routing: Assignment Rules & Auto-Response | S2-02, S2-03.b (completes), S2-04 | Sales & Marketing Applications | ~12% | All channels route correctly; auto-response fires; no internal case triggers; public site reachable in incognito
Sprint 2 | Week 8 | Flow Builder: Loop Protection Engine | S2-05 | Process Automation & Flow Builder | ~16% | OOO subject closes Case; legitimate subject stays New; Constraint Encounter written
Sprint 3 | Week 9 | Entitlements & SLA Milestones | S3-01 | Service & Support / Entitlements | ~11% | Urgent Case shows 4:00:00 countdown; clock stops on first response
Sprint 3 | Week 10 | Red Alert Escalation Flow | S3-02, S3-04 | Process Automation & Flow Builder | ~16% | Notification fires within threshold; assigned cases ignored; Chatter feed empty
Sprint 3 | Week 11 | Reports, Dashboards & Data Storytelling | S3-03 | Analytics, Reports & Dashboards | ~9% | SLA approx 78%; Veterans = 10; open cases = 10; dashboard visible to Elena only
Sprint 3 | Week 12 | Org Handover, Final Audit & Capstone Demo Day | S3-04 | Change Management & Maintenance | ~7% | All 4 smoke tests pass; security intact; 12 Decision Log entries published; Demo Day attended
LOAD NOTE | Week 7 now carries three stories (S2-02, S2-03.b completion, S2-04) while Week 5 carries one. Cohort 0 is past this point — the testing record should decide whether S2-02 returns to Week 5 (where the detail sheet marked it Complete) or Week 5 absorbs part of S2-03.a. Flagged rather than resolved.
DOMAIN CHECK | All nine Administrator exam domains remain covered. No domain lost coverage as a result of these moves.

## GT ACT Cleanup
Guided Trail Blueprint — ACT naming cleanup | ACT was the predecessor program; Foundations Trail replaced it. 14 references need updating.
Section | Current text (abbreviated) | Recommended replacement | Note
1.1 Difference callout | "ACT taught you what to build and showed you how." | "The Foundations Trail taught you what to build and showed you how." | Straight rename.
1.2 Who Is Not Ready | "You have not yet passed the Salesforce Administrator exam. (ACT is your next step.)" | "...(The Foundations Trail is your next step.)" | Straight rename.
1.4 Heading | "How the Guided Trail Differs from ACT" | "How the Guided Trail Differs from the Foundations Trail" | Straight rename.
1.4 Portfolio row | "same framework as ACT, but now complete and employer-ready" | "same framework as the Foundations Trail, but now complete and employer-ready" | Straight rename.
3.1 Project Overview | "In ACT, you built the HCH Salesforce environment from scratch by following Build With Me videos." | "In the Foundations Trail, you built the HCH environment from scratch with Build With Me videos." | Straight rename.
3.1 HCH at a Glance | "Current State: A working Salesforce org built by their previous admin (you, in ACT)." | "...(you, in the Foundations Trail)." | Straight rename.
3.2 Heading | "The Shift from ACT to Guided Trail" | "The Shift from the Foundations Trail to the Guided Trail" | Straight rename.
3.2 Opening line | "The most important difference between ACT and the Guided Trail is not technical complexity." | "...between the Foundations Trail and the Guided Trail..." | Straight rename.
3.2 Comparison table | Column header "In ACT..." | "In the Foundations Trail..." | Straight rename.
3.3 Org Setup | "If you completed ACT, you already have a Salesforce Developer Edition org with the HCH build." | "If you completed the Foundations Trail, you already have..." | Straight rename.
3.3 Org Setup | "If you are entering the Guided Trail without having completed ACT, your coach will provide access to a pre-built HCH starter org that replicates the ACT output." | "...without having completed the Foundations Trail, your coach will provide a pre-built HCH starter org that replicates the Foundations Trail output." | IMPORTANT — this starter org is the primary GT entry path, since most GT learners are externally certified. It needs to be built and seeded, not just described.
3.3 Decision Log | "Keep your Admin Decision Log from ACT. Guided Trail entries begin at #13 (or #1 if you are new)." | "...from the Foundations Trail. Guided Trail entries begin at #13 (or #1 if you are new)." | Numbering is correct — Foundations produces exactly 12 entries.
3.3 Portfolio | "Your Experience Cloud portfolio site continues from ACT." | "...continues from the Foundations Trail." | Straight rename.
ADDITIONAL DRIFT FOUND
Sprint 2 Week 5 | GT uses inboxes intake@ / urgent@ / info@ | FT matrix uses info@ / help@ / grants@ | Same fictional org, two different inbox sets. Pick one. The plus-addressing workaround applies to GT identically.
Sprint 2 Week 7 | GT routes on priority + service category and creates a Veteran Services Queue | FT uses one rule with three ordered record-type entries | Both are valid; they teach different things. Decide deliberately rather than by drift.