## Sprint 2 Revised
Foundations Trail — Sprint 2 Revised Stories | Constraints & workarounds applied · supersedes Sprint 2 rows in Traceability Matrix v1.0
Sprint | Week | Story ID | Story Title | Persona / Role | User Story | Exam Domain | Exam Wt. | Scenario # | Scenario Title | Given | When | Then | Environment | Platform Constraint | Workaround | Build / Config Notes | Pass / Fail Test | Added Deliverable | Status | Change Note
Sprint 2 | Week 5 | S2-01 | Multi-Channel Email-to-Case | Support Representative | I want emails sent to info@, help@, and grants@ to automatically become Salesforce Cases so I can start triage immediately without manual transcription. | Service & Support Applications | ~11% | AC-1 | Email Creates Case | Client sends an email to the General/Utility routing address | Salesforce processes the inbound email via Email-to-Case | A new Case is created with Status = New and Origin = Email, assigned to General Support Queue | Learner dev org | Nobody owns mailboxes at hch.org. Email-to-Case routing addresses require inbox access to complete verification, so the three named addresses in the original story cannot exist. | Gmail plus-addressing: name+info@gmail.com, name+help@gmail.com, name+grants@gmail.com. All deliver to one inbox; each verifies independently as a distinct routing address. Multi-channel build stays intact with no domain required. | Email-to-Case enabled in Service Setup; 3 routing addresses via plus-addressing; Create Task from Email = OFF; HTML Email = ON; Contact matching = Use Default if No Match Found; 3 Case Record Types; 4 Queues with Staff users as members | Send test email to each of the 3 plus-addresses. Verify correct Case Record Type and Queue; no duplicate on reply. |  | Revise | Routing addresses changed from hch.org to learner plus-addresses. Story intent unchanged.
[8 empty] | AC-2 | Correct Channel Routing | Client sends an email to the Veteran Services routing address | Email is processed by Email-to-Case | Case is created with Record Type = Veteran Services and routed to Veteran Services Queue | Learner dev org | [5 empty] | Revise
[8 empty] | AC-3 | Threading on Reply — RETARGETED | An existing Case has had an outbound auto-response sent to the client address | The learner replies to that notification from a second personal email address | The reply attaches to the original Case as an Email Message record — no duplicate Case is created | Learner dev org | Cannot be simulated. Requires a genuine outbound notification and a genuine inbound reply; no autoresponder is available to produce it. | Learner sends the reply manually from a second personal address they control, then verifies the Email Message record on the original Case. Fiddly but fully provable. | Verify Email Message related list on the Case; confirm Case count did not increase | Reply from second address → attaches to original Case; Case count unchanged |  | Revise | Retargeted rather than deleted. Original wording assumed a client-side auto-reply that cannot be produced.
Sprint 2 | Week 7 | S2-02 | Automated Queue Routing | Support Representative | I want incoming Cases to be automatically routed to the correct specialist queue based on the service type so no case sits in the wrong queue. | Sales & Marketing Applications | ~12% | AC-1 | Record Type Routing | A new Case is created with Record Type = Housing Support | The Case Assignment Rule evaluates the record | Case is assigned to the Housing Support Queue with no manual assignment | Learner dev org | None. |  | ONE Case Assignment Rule with 3 ordered entries (Utility, Housing, Veteran Services); default owner = General Support Queue; entries evaluate top-down, first match wins | Create one case of each Record Type → correct queue. Create case matching no criteria → General Support Queue. |  | Move | OWNERSHIP MOVED: Week 5 → Week 7. Week 5 owns record types, queues and Email-to-Case (the containers). Week 7 owns the routing logic that fills them, paired with S2-04.
[8 empty] | AC-2 | Single Active Rule | Admin attempts to activate a second Case Assignment Rule | Admin clicks Activate on the second rule | The first rule is automatically deactivated — only one Assignment Rule per object can be active at a time | Learner dev org | [5 empty] | Move
[8 empty] | AC-3 | Default Queue for No Match | A Case is created that matches no Assignment Rule entry criteria | The Assignment Rule evaluates and finds no matching entry | Case is assigned to the General Support Queue (the rule default owner) | Learner dev org | [5 empty] | Move
Sprint 2 | Week 6 | S2-03.a | Public Web-to-Case Intake Form | Community Member in crisis | I want to submit a help request via a web form so I can request assistance even when the physical office is closed. | Service & Support Applications | ~11% | AC-1 | Form Submission & Case Creation | Community member completes the Utility Assistance web form in a browser | User clicks Submit | A Case is created with Record Type = Utility Assistance, assigned to Utility Assistance Queue; client receives auto-response with Case Number | Learner dev org | None for the form itself. |  | Web-to-Case enabled; HTML form with First Name, Last Name, Email, Phone, Subject, Description; Record Type ID as hidden input; HTML required = ON; Validation Rule for server-side enforcement | Submit with known contact email → Case created and linked. Submit with unknown email → Case created, unlinked. |  | Keep | Split confirmed. .a ships the form and its hidden record type and is provable without a public site.
[8 empty] | AC-2 | Hidden Record Type Enforcement | Form submitted with no visible Record Type field | Salesforce receives the POST request | Case Record Type is set to Utility Assistance via hidden input — cannot be manipulated client-side | Learner dev org | [5 empty] | Keep
[8 empty] | AC-3 | Contact Match | Form submitted with an email that matches an imported Contact | Salesforce processes the submission | Case is automatically linked to the matching Contact record | Learner dev org | [5 empty] | Keep
Sprint 2 | Week 7 | S2-03.b | Create Public Case Intake Platform | Community Member in crisis | I want a platform that lets me submit a case when I have an immediate need of assistance. | Service & Support Applications | ~11% | AC-1 | Public Access | A community member needs to submit a case via a form | The community member navigates to the public experience URL | The member reaches the site and is not blocked from its contents | Learner dev org | Guest user access AND guest API access must both be enabled. Guest permissions are deliberately restrictive, and a missing Create permission on Case fails silently — the form appears to work and no record is created. | Verify in an incognito window. Add an explicit check that the guest user profile has Create on Case before testing submission — the single most common cause of a silent failure. | LWR digital experience site created; guest user access enabled; guest API access enabled; Web-to-Case form added to the site | Navigate in incognito → landing page loads. Submit → Case created. Confirm guest profile has Create on Case. |  | Split | FORMALIZED SPLIT from S2-03. Emerged in Cohort 0 testing when the story outgrew its week. Carries its own Definition of Done and its own demo.
[8 empty] | AC-2 | Navigable Landing Page | A community member has accessed the public site | The member is viewing the landing page | The member can see the case form and enter data | Learner dev org | [5 empty] | Split
Sprint 2 | Week 7 | S2-04 | Auto-Response & Routing Notifications | Support Representative | I want clients to automatically receive a confirmation email when their case is created so they know their request was received. | Service & Support Applications | ~11% | AC-1 | Auto-Response on Web Submission | Client submits the Utility Assistance web form | Case is created with Origin = Web | Client receives an automated email: We received your request — Case #[CaseNumber], within minutes | Learner dev org | Developer Edition caps daily outbound email to external addresses. Auto-responses count against that cap, so repeated channel testing produces silent failures that look like broken configuration. | Cap the test plan: one submission per channel, verified, then stop. Teach the learner to read the org email log so they can distinguish a governor limit from a misconfiguration. | Auto-Response Rules scoped to Origin = Web OR Email; one rule per Record Type; templates include the CaseNumber merge field | Submit web form → auto-response received with correct template. Create case with Origin = Phone → no auto-response. |  | Annotate | Constraint documented. Story and acceptance criteria unchanged.
[8 empty] | AC-2 | Channel-Specific Templates | Cases arrive via three different channels (Web, and two email routing addresses) | Auto-Response Rules evaluate the new Case | Each channel receives a template specific to that service type; no cross-channel misfires | Learner dev org | [5 empty] | Annotate
[8 empty] | AC-3 | Internal Cases Not Triggered | A caseworker manually creates a Case directly in Salesforce (Origin = Phone) | Auto-Response Rule evaluates the Case | No auto-response is sent — the Origin filter prevents internal case notifications | Learner dev org | [5 empty] | Annotate
Sprint 2 | Week 8 | S2-05 | Loop Protection Flow (Spam & OOO Filter) | System Administrator | I want to prevent Out of Office and Undeliverable emails from creating Cases so support queues are not flooded with automated ghost records. | Process Automation & Flow Builder | ~16% | AC-1 | OOO Subject Triggers Auto-Close | An email with subject beginning "Automatic reply:" is processed by Email-to-Case | The Case is created and the Record-Triggered Flow evaluates it (After-Save, Created) | Case Status is set to Closed | Learner dev org | No real out-of-office autoresponder is available to fire at the learner org. | Not a blocker. The Flow keys on the Subject field, not on sender intent — the learner sends an email whose subject begins "Automatic reply:" from any address and every criterion is provable as written. | Record-Triggered Flow on Case; Trigger = Created; Optimize = After Save; Decision: Subject CONTAINS "Out of Office" OR "Automatic reply" OR "Undeliverable" (ANY); Update Records: Status = Closed | Test 1: Subject "Automatic reply: test" → Closed. Test 2: "Help, my lights are out" → stays New. Test 3: "OUT OF OFFICE" → Closed. | Constraint Encounter write-up: what the out-of-the-box feature did not handle, what you built to cover it, and what it would have cost Elena — one paragraph in her language. | Revise | RESOLVED CONFLICT: original Then said Status = Needs Review with a Case Comment, while Build Notes and Pass/Fail Test both said Status = Closed. Closed adopted. Also adds the Constraint Encounter deliverable (RESOLVE Explore to Select).
[8 empty] | AC-2 | Legitimate Case Stays Open | An email with subject "Help, my lights are out" creates a Case | The Record-Triggered Flow evaluates the Case | Case Status remains New and routes normally; the Flow takes no action | Learner dev org | [5 empty] | Revise
[8 empty] | AC-3 | Case-Insensitive Matching | An email with subject "OUT OF OFFICE: vacation until Monday" creates a Case | Flow evaluates the Subject field | Case is Closed — the CONTAINS operator is case-insensitive | Learner dev org | [5 empty] | Revise