## Resource Tracker
Foundations Trail — Resource Development Tracker
Transition Trails ¦ Foundations Trail Resources ¦ Version 1.0 ¦ May 2026
ID | Resource Title | Category | Gap Addressed by Foundations Trail | Format / Est. Length | Priority | Status | Owner | Target Date | Foundations Trail Weeks | Production Notes | Done? ✓
BWM-F1 | Getting Your Org Ready | Build With Me Video | Learners entering the program have never navigated Setup or installed a managed package. Week 1 of Foundations Trail drops them directly into NPSP install decisions. | Screen-record / 30–40 min | 1 — Critical | Not Started |  | Pre-Cohort 1 | Week 1 (NPSP install, org naming, org as portfolio artifact) | Cover: Developer Edition signup → Setup nav → App Launcher → Object Manager → AppExchange install → reading install logs. End with learner verifying NPSP Household Account model is active.
BWM-F2 | Objects, Fields, and How Salesforce Thinks | Build With Me Video | Week 2 asks learners to create 4 custom fields and make field-type decisions. Without prior exposure to the standard data model and field types, they follow steps without understanding them. | Screen-record / 45–50 min | 1 — Critical | Not Started |  | Pre-Cohort 1 | Week 2 (custom fields, picklist values), Week 4 (data import field mapping) | Cover: standard objects (Account, Contact, Case) → relationships → field types with nonprofit examples → picklist vs. text deep-dive → OWD conceptual intro. Use a fictional org (not HCH) so it's reusable across cohorts.
BWM-F3 | Reading Salesforce Like a Professional | Build With Me Video | Learners who don't know how to find answers independently slow down in the Foundations Trail and burn coach time. Teaches the research workflow admins actually use. | Screen-record / 25–30 min | 2 — High | Not Started |  | Pre-Cohort 1 | All Foundations Trail weeks (independent problem-solving habit) | Cover: Salesforce Help → Trailhead trail navigation → how to use Penny effectively → when to escalate to Office Hours. Frame as the admin's daily research loop.
BWM-F4 | Your Portfolio Is a Professional Document | Build With Me Video | Week 1 Portfolio Side Quest requires a live Experience Cloud site. Learners who have never set one up cannot complete Week 1 artifacts. | Screen-record / 20–25 min | 2 — High | Not Started |  | Pre-Cohort 1 | Week 1 Portfolio Side Quest (site setup, professional headline) | Cover: Experience Cloud → Digital Experiences setup → template selection → professional headline → how employers read a portfolio site. Connect to Transition Trails brand: portfolio = the product, not homework.
CP-F1 | The Salesforce Data Model in 1 Page | Concept Primer | Sprint 1 builds heavily on the Account → Contact → Case relationship. Learners who haven't internalized the standard model before entering the program work slower and make architecture mistakes. | PDF reference / 1 page | 1 — Critical | Not Started |  | Pre-Cohort 1 | Weeks 1–4 (referenced throughout Sprint 1) | Two columns: (1) Standard model with relationships labeled; (2) How NPSP modifies it (Household Account). This should live in every learner's browser during all of Sprint 1.
CP-F2 | Field Types Decision Guide | Concept Primer | The most common Sprint 1 red flag is learners creating Text fields where Picklists belong. This primer builds the decision habit before they touch Object Manager in the Foundations Trail. | PDF reference / 1–2 pages | 1 — Critical | Not Started |  | Pre-Cohort 1 | Week 2 (custom fields), Week 4 (dirty data import — picklist mismatches) | Two-column table: 'If the data looks like this → use this field type.' Include Text, Number, Date, Picklist, Checkbox, Formula, Lookup. Each row has a HCH-style example.
CP-F3 | The Admin Mindset: Document Everything | Concept Primer | Admin Decision Log starts in Week 1. Learners who haven't been taught the documentation habit write one-line entries that don't pass portfolio review. | PDF reference / 1 page | 1 — Critical | Not Started |  | Pre-Cohort 1 | Week 1 (first Admin Decision Log entries), Foundations Trail all weeks (portfolio quality) | Explain what an Admin Decision Log is and why it exists. Include 3 example entries at different quality levels — weak / adequate / strong — with annotations. Make it feel like professional practice, not homework.
CP-F4 | Platform Foundations Exam Prep Cheat Sheet | Concept Primer | Learners need a structured self-assessment tool to know when they're ready to sit the Platform Foundations exam. Without it, they either sit too early or delay indefinitely. | PDF / 2 pages | 2 — High | Not Started |  | Pre-Cohort 1 | Platform Foundations certification gate (required before Foundations Trail entry) | Domain-by-domain breakdown of Platform Foundations exam. Weights + 3–5 key concepts per domain + self-rating column. Learner uses this alongside Trailhead. Note: do NOT include Admin exam content here — that's the Foundations Trail's job.
PB-F1 | Penny AI Prompt Bank — Foundations Trail | Penny Prompt Bank | Foundations learners don't yet know how to ask precise questions. Without curated starter prompts, they get generic AI answers and give up on self-directed learning. | PDF or in-app list / 10–15 prompts | 2 — High | Not Started |  | Pre-Cohort 1 | All Foundations Trail weeks (self-directed learning habit formed in Foundations carries through) | Organize by concept area: Objects & Data Model, Field Types, Security (OWD/Profiles/FLS), Exam Prep, Documentation/Research. Include instructions: 'Copy, paste, and customize — change the underlined parts to fit your specific question.' See recommendations doc for full prompt list.
EC-F1 | Foundations Trail Exit Checklist | Exit Checklist | Without a structured readiness gate, learners enter Foundations Trail at wildly different knowledge levels. Coaches waste the first two weeks of Foundations Trail bringing some learners up to baseline. | PDF form or Google Form / 3 parts | 1 — Critical | Not Started |  | Pre-Cohort 1 | Week 1 (this IS the entry requirement — if they can't answer Q5, they're not ready) | Part 1: Credential (Platform Foundations cert — required). Part 2: 5 written questions (answers reviewed by coach). Part 3: Portfolio check (site URL, headline, one section started). Q5 maps directly to Week 1 Discussion Prompt — the NPSP Household Account question.

## Production Sequence
Foundations Trail — Recommended Production Sequence
Build resources in this order to maximise learner readiness before Cohort 1. Items ranked 1–3 unblock Week 1. Items 4–7 prevent the most common Sprint 1 red flags. Items 8–10 improve the Foundations Trail experience but are not blocking.
Build Order | ID | Title | Category | Why This Order | Estimated Effort | Status
1 | CP-F3 | The Admin Mindset: Document Everything | Concept Primer | Needed from Week 1 Day 1. Fastest to produce (30–45 min to write). Highest leverage per minute of effort. | 30–45 min | Not Started
2 | BWM-F1 | Getting Your Org Ready | Build With Me Video | Removes the most common Week 1 friction (NPSP install confusion, wrong org type). Without this, coaches spend Week 1 Office Hours on setup not concepts. | 2–3 hrs (record + edit) | Not Started
3 | CP-F1 | The Salesforce Data Model in 1 Page | Concept Primer | The single reference document learners should have open throughout all of Sprint 1. Quick to produce; used in every Sprint 1 week. | 2–3 hrs (design) | Not Started
4 | CP-F2 | Field Types Decision Guide | Concept Primer | Directly prevents the #1 Sprint 1 red flag (Text fields where Picklists belong). Learner reads this before Week 2. | 1–2 hrs | Not Started
5 | BWM-F2 | Objects, Fields, and How Salesforce Thinks | Build With Me Video | The conceptual prerequisite for every custom field learners create in Weeks 1–4. Makes Week 2 a review, not a first exposure. | 3–4 hrs (record + edit) | Not Started
6 | PB-F1 | Penny AI Prompt Bank | Penny Prompt Bank | Can be drafted in a single session. Immediately reduces unproductive Penny queries and builds the research habit that Foundations Trail depends on. | 1–2 hrs | Not Started
7 | EC-F1 | Foundations Trail Exit Checklist | Exit Checklist | Defines the program's done state. Everything in the Foundations Trail is scaffolding toward this checklist. Build early so coaches can reference it when guiding learners. | 2–3 hrs (questions + form) | Not Started
8 | BWM-F3 | Reading Salesforce Like a Professional | Build With Me Video | Important habit builder but less urgent than org literacy and data model. Learners can muddle through documentation in early Foundations Trail weeks; this raises the floor long-term. | 2–3 hrs (record + edit) | Not Started
9 | BWM-F4 | Your Portfolio Is a Professional Document | Build With Me Video | Needed before Week 1 Portfolio Side Quest, but only blocking if learner has never touched Experience Cloud. Many learners from the Guided Trail have this. | 2 hrs (record + edit) | Not Started
10 | CP-F4 | Platform Foundations Exam Cheat Sheet | Concept Primer | Valuable but learners can build their own from Trailhead. Lower production priority because Trailhead content covers this adequately in the short term. | 2–3 hrs | Not Started
Priority Bands
Items 1–3: Unblock Week 1 — build these first
Items 4–7: Prevent the most common Sprint 1 red flags
Items 8–10: Experience improvements — not blocking

## FT Gap Map
Foundations Trail → Foundations Trail Gap Map
Maps each Foundations Trail week's entry assumption to the Foundations Trail resource that covers it. A learner missing any 'Critical' resource will create friction for coaches in the corresponding Foundations Trail week.
Foundations Trail Week | Build Activity | Entry Assumption | Risk If Gap Exists | Foundations Resource | Priority
Week 1 | NPSP install + org setup + first Decision Log entry | Learner knows what a Developer Edition org is, can navigate Setup, and knows NPSP is a managed package from AppExchange. | Coach spends all of Office Hours on setup instead of concepts. Learner installs NPSP without verifying Household Account model is active. | BWM-F1 + CP-F3 | Critical
Week 2 | Create 4 custom Contact fields with correct field types | Learner understands the difference between Text, Picklist, Date, and Checkbox fields, and can explain why field type is a design decision. | Learner creates Text fields where Picklists belong. Sprint 1 red flag: no understanding of why field type matters for import and reporting. | BWM-F2 + CP-F2 | Critical
Week 2 | Configure Role Hierarchy and OWD = Private | Learner has a working mental model of OWD, Profiles, and Role Hierarchy as distinct layers of Salesforce security. | Learner clicks through security config without understanding what they're building. Security test in Week 2 produces results they can't explain. | BWM-F2 (OWD conceptual intro section) | Critical
Week 3 | Clean legacy CSV and import via Data Import Wizard | Learner understands what a picklist value mismatch means and can recognize date format errors. Understands field-level API names. | Learner cannot interpret the import error log. 5–10 records fail with cryptic errors they can't diagnose without field type foundation. | CP-F2 + CP-F1 | Critical
Week 4 | Write Admin Decision Log entries for Portfolio | Learner knows what an Admin Decision Log entry looks like and has been writing them since Week 1. | Learner's Decision Log entries are one-liners that don't pass portfolio review. Coach must remediate documentation quality at Week 4 Demo. | CP-F3 | Critical
Week 4 | Sprint 1 Demo + Portfolio Side Quest (site live) | Learner has an active Experience Cloud portfolio site with a professional headline and at least one section. | Learner has no portfolio site and cannot present their Sprint 1 artifacts. Demo Day is incomplete. | BWM-F4 | High
All Weeks | Self-directed problem-solving (no hand-holding between sessions) | Learner has a research workflow: Trailhead → Help → Penny → Office Hours. Does not contact coach for every stuck moment. | Coaches receive Slack messages for every small problem. Office Hours become remedial rather than discussion-based. | BWM-F3 + PB-F1 | High
Foundations Trail Entry Gate | Platform Foundations certification (prerequisite) | Learner has passed Platform Foundations before starting Week 1. | Learner joins Foundations Trail without foundational Salesforce literacy. Every week is harder than it should be. Exam pass rate drops. | CP-F4 + EC-F1 | Critical

## Penny Prompt Bank
Foundations Trail — Penny AI Prompt Bank (PB-F1)
These starter prompts are designed for Foundations Trail learners who don't yet know how to ask precise Salesforce questions. Instructions for learners: Copy the prompt, paste it into Penny, and customize the underlined/bracketed parts to fit your specific situation.
# | Concept Area | Prompt Text | What Good Looks Like (Coach Reference)
1 | Objects & Data Model | I'm just learning Salesforce. Can you explain the difference between an Account and a Contact like you're talking to someone who has never seen a CRM before? Then give me one example from a nonprofit context. | Penny explains Account as the organization/household and Contact as the individual person, with an example like 'Martinez Household' containing Carlos, Maria, and Sofia.
2 | Objects & Data Model | What is the difference between a lookup relationship and a master-detail relationship in Salesforce? Which one should I use if I want to see a Contact's Cases but also want the ability to delete the Contact without losing the Cases? | Penny explains that master-detail deletes child records when parent is deleted (lookup does not), and recommends lookup for Cases-to-Contact.
3 | Objects & Data Model | I keep hearing the term 'NPSP Household Account Model.' In plain English, how does NPSP change the standard relationship between a Contact and an Account in Salesforce? | Penny explains that standard Salesforce links Contacts to business Accounts, while NPSP auto-creates a 'Household Account' (e.g., 'Martinez Household') that groups family members together.
4 | Field Types | I'm building a custom field to track whether a client is a veteran. My options are a Text field, a Picklist, or a Checkbox. Walk me through the pros and cons of each, and then tell me which one the Salesforce Admin exam would consider best practice and why. | Penny explains Picklist enforces controlled values (Yes/No/Unknown), Checkbox only allows Yes/No (no Unknown state), and Text is too freeform. Best practice = Picklist because it enables clean filtering and reporting.
5 | Field Types | Why does it matter what field type I choose when I'm just storing data? Can't I put almost anything in a Text field? | Penny explains that field type affects how data can be filtered, reported on, imported, and validated — and that using Text instead of Picklist breaks reports, import matching, and future automation.
6 | Security | I keep hearing the words OWD, Role Hierarchy, Profiles, and Permission Sets in Salesforce training. Can you give me a one-sentence plain-English definition of each one, and then explain how they work together in one short paragraph? | Good answer: OWD = default sharing baseline; Role Hierarchy = grants upward visibility; Profiles = what you can do; Permission Sets = additions on top of profiles. Together they form layered access control.
7 | Security | If I set Case OWD to Private, what exactly does that mean for who can see a case record? And how does the Role Hierarchy change that? | Penny explains: OWD Private means only the record owner can see it. Role Hierarchy means people above the owner in the hierarchy also gain visibility — so a Program Director can see a Caseworker's cases.
8 | Exam Prep | I'm studying for the Salesforce Platform Foundations certification. I just finished reading about the standard Salesforce data model. Can you give me three practice questions the way they'd appear on the actual exam, and then explain the correct answer and why the other options are wrong? | Penny provides scenario-based questions with 4 answer options each, explains the correct choice, and identifies why the distractors are plausible but wrong.
9 | Exam Prep | I scored 65% on my Platform Foundations practice test. I got most of the data model questions right but struggled with the security questions. Can you give me a focused review of the 3–4 most important security concepts I need to know for this exam? | Penny focuses on OWD, Role Hierarchy, Profiles, FLS, and Sharing Rules — the core security stack that appears on the exam.
10 | Documentation | I found a Salesforce Help article but I can't tell if it applies to my situation. The article title is: [paste title here]. What 3 questions should I ask myself to figure out if this article is relevant to what I'm trying to do? | Good Penny response prompts: (1) Does it mention the same feature/object I'm working with? (2) Does it match my edition/org type? (3) Does the scenario described match my use case?
11 | Documentation | I'm stuck on a Salesforce configuration problem and I've read the Help article twice and I still don't understand it. Before I ask my coach, what steps should I take to try to solve it myself? | Good answer: (1) Restate the problem in one sentence; (2) Search Trailhead for a related module; (3) Ask Penny to explain the concept in a different way; (4) Try it in the org and observe what happens; (5) Then escalate.
12 | Decision Log | I just made a configuration decision in my Salesforce org that I need to document. The decision was: [describe what you decided]. Can you help me write a strong Admin Decision Log entry that explains what I chose, why I chose it, and what the alternative was? | A strong Penny-assisted entry includes: what was decided, why that option (business reason + technical reason), what the alternative was and why it was rejected, and any downstream implications.
13 | Portfolio | I need to write a professional headline for my Salesforce portfolio site. I'm a career-changer with a background in [previous field]. I just earned my Platform Foundations certification and I'm working toward my Admin certification. Can you suggest 3 headline options that would appeal to a hiring manager? | Good headlines position the learner's prior background as an asset, emphasize real org work, and avoid generic phrases like 'passionate about Salesforce.'

## Exit Checklist
Foundations Trail — Exit Checklist (EC-F1)
Every learner completes this checklist before entering the program. The coach reviews Part 2 written answers. A learner who cannot answer Q5 is not ready for Week 1 — the NPSP Household Account question maps directly to the Week 1 Office Hours discussion prompt.
Part 1 — Credential Gate (Required)
This question has one correct answer. Without Platform Foundations certification, entry to Foundations Trail is not permitted.
# | Question | Learner Answer | Pass Criteria | Coach ✓
Q1 | Have you passed the Salesforce Platform Foundations certification? Please paste your credential URL from your Trailhead profile. |  | Credential URL provided + verified against Trailhead profile. | ☐
Part 2 — Technical Readiness (Written Answers — Coach Reviews)
Learner writes answers in their own words. These are not trick questions. Acceptable answers demonstrate understanding, not memorization. Q5 is the most important — it maps directly to Week 1 Discussion Prompt.
# | Question | Learner Answer | What a Good Answer Includes | Coach ✓
Q2 | What is the difference between a Profile and a Permission Set in Salesforce? |  | Profile = baseline set of permissions assigned to every user in that group. Permission Set = additions on top of a profile for specific users. A user has one profile; they can have many permission sets. | ☐
Q3 | A nonprofit wants to track whether a client receives food assistance, housing assistance, both, or neither. What Salesforce field type would you recommend for this and why? |  | Multi-select Picklist (allows multiple values from a controlled list). Bonus: explains why Text is wrong (no enforcement), why Checkbox is wrong (only Yes/No), and why controlled values matter for reporting. | ☐
Q4 | You need to make sure caseworkers can only see the cases they personally own — not each other's cases. What Salesforce feature controls this? |  | Organization-Wide Defaults (OWD) set to Private for Cases. Acceptable: also mentions Role Hierarchy grants upward visibility to managers. | ☐
Q5 | What is a Developer Edition org, and why does Foundations Trail require a new dedicated one rather than a Trailhead Playground? |  | Developer Edition = free, full-featured Salesforce org. Trailhead Playgrounds reset and are shared infrastructure. Foundations Trail requires a dedicated org because it's a professional artifact the learner builds over 12 weeks — it becomes their portfolio. | ☐
Q6 | In the NPSP Household Account model, if you create a new Contact called 'Carlos Martinez' without specifying an Account, what happens automatically? |  | CRITICAL QUESTION — maps to Week 1 Discussion Prompt. NPSP automatically creates a 'Martinez Household' Account and links Carlos to it. If the learner cannot answer this, they are not ready for Week 1. | ☐
Part 3 — Portfolio Readiness
The portfolio site must be live before Week 1. Week 1 Portfolio Side Quest adds artifacts to an existing site — it does not set one up.
# | Portfolio Check | Learner Answer / URL | Pass Criteria | Coach ✓
P1 | Paste the public URL of your Experience Cloud portfolio site. |  | URL resolves to a live Salesforce Experience Cloud site (not a playground). | ☐
P2 | Does your portfolio site have a professional headline that includes your name and career goal? |  | Headline is visible on the homepage and references Salesforce administration or nonprofit technology. | ☐
P3 | Has at least one section (About, Projects, or Contact) been started with real content? |  | At least one section exists with non-placeholder text. 'Coming soon' is not acceptable. | ☐
Coach Sign-Off
Learner Name:
Coach Name:
Review Date:
Entry to Foundations Trail Approved? (Yes / No / Not Yet — Reason):